## Risk Matrix
CYBERSECURITY RISK MATRIX
Risk Assessment Framework for Small Businesses · Himanshu Soni · 2025–2026
# | Risk / Threat | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Level | Priority | Mitigation Controls
1 | Phishing Attacks | 5 | 4 |  | High | Immediate | Email filters, MFA, Security awareness training
2 | Ransomware | 4 | 5 |  | High | Immediate | Regular backups, Endpoint security, Patch management
3 | Insider Threats | 3 | 5 |  | High | Urgent | RBAC, Access monitoring, Least privilege policy
4 | Weak Passwords | 5 | 4 |  | High | Immediate | MFA, Password managers, Strong password policy
5 | Unpatched Software | 4 | 4 |  | High | Urgent | Automated patch mgmt, Vulnerability scans
6 | Data Breach | 3 | 5 |  | Critical | Immediate | Encryption, DLP tools, Access control
7 | Social Engineering | 4 | 4 |  | High | Urgent | Employee training, Verification protocols
8 | DDoS Attacks | 2 | 4 |  | Medium | Plan | CDN, Rate limiting, Incident response plan
9 | Third-party Risks | 3 | 3 |  | Medium | Monitor | Vendor assessments, Contract security clauses
10 | Misconfiguration | 4 | 3 |  | Medium | Plan | Config audits, IaC security, CIS benchmarks
RISK LEVEL SCALE
1 – 5 | Low | Monitor — acceptable risk, periodic review
6 – 10 | Medium | Plan — implement controls within 90 days
11 – 15 | High | Respond Soon — implement controls within 30 days
16 – 25 | Critical | Immediate Action — resolve within 7 days

## Risk Heat Map
RISK HEAT MAP — THREAT SEVERITY MATRIX
Likelihood (X-axis, 1–5) vs Impact (Y-axis, 1–5) · Score = Likelihood × Impact
Impact \ Likelihood | Likelihood = 1 | Likelihood = 2 | Likelihood = 3 | Likelihood = 4 | Likelihood = 5
Impact = 5 | 5 | 10 | 15 Insider Threats | 20 Ransomware | 25
Impact = 4 | 4 | 8 | 12 Social Eng. | 16 Unpatched SW | 20 Phishing & Passwords
Impact = 3 | 3 | 6 | 9 | 12 | 15
Impact = 2 | 2 | 4 | 6 | 8 | 10
Impact = 1 | 1 | 2 | 3 | 4 | 5

## Mitigation Plan
MITIGATION PLAN — SECURITY CONTROLS
Threat | Control Type | Control Measure | Implementation Timeline | Responsible Party | Status
Phishing Attacks | Technical | Email filtering & anti-spam gateway | Immediate | IT Admin | Planned
Phishing Attacks | Administrative | Security awareness training for all staff | 30 Days | HR + IT | Planned
Phishing Attacks | Technical | Multi-Factor Authentication (MFA) | Immediate | IT Admin | Planned
Ransomware | Technical | Automated daily encrypted backups | Immediate | IT Admin | Planned
Ransomware | Technical | Endpoint detection and response (EDR) | 30 Days | IT Admin | Planned
Ransomware | Technical | Regular patch management cycle | Ongoing | IT Admin | Planned
Insider Threats | Technical | Role-Based Access Control (RBAC) | 30 Days | IT + Mgmt | Planned
Insider Threats | Technical | Activity monitoring & audit trails | 60 Days | IT Admin | Planned
Insider Threats | Administrative | Least privilege policy enforcement | Immediate | Management | Planned
Weak Passwords | Technical | Password manager deployment | Immediate | IT Admin | Planned
Weak Passwords | Administrative | Enforce strong password policy | Immediate | IT + HR | Planned
Unpatched Software | Technical | Automated vulnerability scanning | 30 Days | IT Admin | Planned
Unpatched Software | Technical | Patch management tool implementation | 30 Days | IT Admin | Planned